## Summary
DMHR Status - Nov 2010
Koniambo Power Station (C004) - Doosan | [10 empty] | 2010-11-26
CWP No. | Discipline | Description | Weight (%) | This Month Weight (%) |  |  | Total Dmhr | Up to Last Month | This Month |  |  | PF | Remarks
|  |  |  | Up to Last Month | Actual | To Date |  |  | Actual | To Date | To Go
CWP |  | Civil | 11.56% | 18.79% | 9.058% | 27.85% | 355920 | 66893.2 | 32240 | 99133.2 | 256786.8
|  | Mechanical | 75.08% | 16.16% | 12.72% | 28.88% | 2310934 | 57509.4 | 45285 | 102794.4 | 2208139.6
|  | Electrical | 13.35% | 0.528% | 0.09553% | 0.6235% | 411045 | 1879.2 | 340 | 2219.2 | 408825.8
|  | Total CWP | 100% | 35.48% | 21.88% | 57.36% | 3077899 | 126281.8 | 77865 | 204146.8 | 2873752.2
Extra Works |  | Civil | [5 empty] | 5147 | 2517 | 7664
|  | Mechanical | [5 empty] | 3244 | 1994 | 5238
|  | Electrical | [6 empty] | 0 | 0
|  | Total Extra Works |  |  |  |  | 0 | 8391 | 4511 | 12902 | 0
Agreed Suspension Works |  | Civil | [5 empty] | 63 |  | 63
|  | Mechanical | [5 empty] | 1036 |  | 1036
|  | Electrical | [7 empty] | 0
|  | Total Agreed Suspension Works |  |  |  |  | 0 | 1099 | 0 | 1099 | 0
Sub Total |  | Civil |  |  |  |  | 355920 | 72103.2 | 34757 | 106860.2 | 256786.8 | 0
|  | Mechanical |  |  |  |  | 2310934 | 61789.4 | 47279 | 109068.4 | 2208139.6 | 0
|  | Electrical |  |  |  |  | 411045 | 1879.2 | 340 | 2219.2 | 408825.8 | 0
|  | Total |  |  |  |  | 3077899 | 135771.8 | 82376 | 218147.8 | 2873752.2 | 0
Infrastructural Works |  | Civil | [5 empty] | 1032.6 | 1820 | 2852.6
|  | Mechanical | [5 empty] | 8322.8 | 4500 | 12822.8
|  | Electrical | [5 empty] | 7959 | 3810 | 11769
|  | Total Infrastructural Works |  |  |  |  | 0 | 17314.4 | 10130 | 27444.4 | 0
Total |  | Civil |  |  |  |  | 355920 | 73135.8 | 36577 | 109712.8 | 256786.8 | 0
|  | Mechanical |  |  |  |  | 2310934 | 70112.2 | 51779 | 121891.2 | 2208139.6 | 0
|  | Electrical |  |  |  |  | 411045 | 9838.2 | 4150 | 13988.2 | 408825.8 | 0
|  | Total |  |  |  |  | 3077899 | 153086.2 | 92506 | 245592.2 | 2873752.2 | 0
* Claim 2 parts of direct manhours which are CWP and Extra Works. Total Claimed manhour in this month : | [8 empty] | 82376

## CWP (Monthly)
DMHR Status - Month of Nov
[13 empty] | 2010-10-22 | Cutoff date | 2010-11-26
|  | Koniambo Power Station (C004) - Doosan | Koniambo Power Station (C004) - Doosan | [8 empty] | 2010-11-26 |  | Weeks | 5
| Name | WSN |  |  |  |  | Discipline | Total Dmhr | Up to Last Month | Man Hours |  |  | Remark |  | Fixed
|  |  | wp |  |  | CWP | [8 empty] | W39 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
[10 empty] | Actual | To Date | To Go | time axis 2010-09-18 to 2012-07-28
[7 empty] | Mechanical | 2310934 | 57509.4 | 45285 | 102794.4 | 2208139.6
m | Boiler 1&2 Drum Lifting Completion | 01 | 01 | 01-18-420-104 | ERECT STRUCTURAL STEEL CFB1 |  |  | 83286 | 45633.4 | 24860 | 70493.4 | 12792.6 |  |  | 2010-09-18: 28809.4; 2010-10-16: 16824; 2010-10-23: 3790; 2010-10-30: 4360; 2010-11-06: 5070; 2010-11-13: 5005; 2010-11-20: 6635
m |  | 01 | 01 | 01-18-420-204 | ERECT STRUCTURAL STEEL CFB2 |  |  | 83283 | 11876 | 16135 | 28011 | 55272 |  |  | 2010-09-18: 2810; 2010-10-16: 9066; 2010-10-23: 2150; 2010-10-30: 3035; 2010-11-06: 3410; 2010-11-13: 3660; 2010-11-20: 3880
m |  | 01 | 01 | 01-68-420-105 | ERECT ST DRUM PRESS PARTS & WATERWALLS CFB 1 |  |  | 18495 | 0 | 0 | 0 | 18495
m |  | 01 | 01 | 01-68-420-205 | ERECT ST DRUM PRESS PARTS & WATERWALLS CFB 2 |  |  | 14334 | 0 | 0 | 0 | 14334
[8 empty] | 199398 | 57509.4 | 40995 | 98504.4 | 100893.6 |  |  | 31619.4 | 25890 | 5940 | 7395 | 8480 | 8665 | 10515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | Boiler 1&2 Hydro Test Completion | 02 | 02 | 02-68-420-105 | ERECT ST DRUM PRESS PARTS & WATERWALLS CFB 1 |  |  | 182170 | 0 | 0 | 0 | 182170
m |  | 02 | 02 | 02-68-420-110 | ERECT BOILER COMPONENTS CFB1 INCLUDE FBHE |  |  | 11363 | 0 | 0 | 0 | 11363
m |  | 02 | 02 | 02-68-420-205 | ERECT ST DRUM PRESS PARTS & WATERWALLS CFB 2 |  |  | 186339 | 0 | 0 | 0 | 186339
m |  | 02 | 02 | 02-68-420-210 | ERECT BOILER COMPONENTS CFB 2 INCLUDE FBHE |  |  | 10854 | 0 | 0 | 0 | 10854
[8 empty] | 390726 | 0 | 0 | 0 | 390726 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | Boiler 1&2 Mechanical Completion | 03 | 03 | 03-18-420-104 | ERECT STRUCTURAL STEEL CFB1 |  |  | 50217 | 0 | 0 | 0 | 50217
m |  | 03 | 03 | 03-18-420-204 | ERECT STRUCTURAL STEEL CFB2 |  |  | 39236 | 0 | 0 | 0 | 39236
m |  | 03 | 03 | 03-68-420-110 | ERECT BOILER COMPONENTS CFB1 INCLUDE FBHE |  |  | 133173 | 0 | 0 | 0 | 133173
m |  | 03 | 03 | 03-68-420-112 | START UP BURNER FUEL PIPING SOOT BLOWER SERVICE PIPING AIR & WATER CFB1 |  |  | 1297 | 0 | 0 | 0 | 1297
m |  | 03 | 03 | 03-68-420-120 | ERECT FABRIC FILTER ID FANS CFB 1 |  |  | 34395 | 0 | 0 | 0 | 34395
m |  | 03 | 03 | 03-68-420-136 | BOTTOM FLY ASH SILOS ASH HANDLING CFB 1 |  |  | 6297 | 0 | 0 | 0 | 6297
m |  | 03 | 03 | 03-68-420-210 | ERECT BOILER COMPONENTS CFB 2 INCLUDE FBHE |  |  | 133681 | 0 | 0 | 0 | 133681
m |  | 03 | 03 | 03-68-420-212 | START UP BURNER FUEL PIPING SOOT BLOWER SERVICE PIPING AIR & WATER CFB2 |  |  | 1297 | 0 | 0 | 0 | 1297
m |  | 03 | 03 | 03-68-420-220 | ERECT FABRIC FILTER ID FANS CFB 2 |  |  | 35363 | 0 | 0 | 0 | 35363
m |  | 03 | 03 | 03-68-420-236 | BOTTOM FLY ASH SILOS ASH HANDLING CFB 2 |  |  | 6297 | 0 | 0 | 0 | 6297
m |  | 03 | 03 | 03-68-422-120 | EMER BFWP ELEVATOR MACHINERY CFB 1 |  |  | 28917 | 0 | 0 | 0 | 28917
m |  | 03 | 03 | 03-68-422-220 | EMER BFWP ELEVATOR MACHINERY CFB 2 |  |  | 28918 | 0 | 0 | 0 | 28918
m |  | 03 | 03 | 03-68-475-130 | COAL HANDLING SYSTEM EQUIPMENT CFB 1 |  |  | 48530 | 0 | 0 | 0 | 48530
m |  | 03 | 03 | 03-68-475-230 | COAL HANDLING SYSTEM EQUIPMENT CFB 2 |  |  | 48530 | 0 | 0 | 0 | 48530
m |  | 03 | 03 | 03-68-476-132 | LIMESTONE HANDLING SYSTEM EQUIPMENT CFB 1 & 2 |  |  | 12561 | 0 | 0 | 0 | 12561
[8 empty] | 608709 | 0 | 0 | 0 | 608709 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | Boiler 1&2 Fabric Filter Complettion | 04 | 04 | 04-68-420-120 | ERECT FABRIC FILTER ID FANS CFB 1 |  |  | 25959 | 0 | 0 | 0 | 25959
m |  | 04 | 04 | 04-68-420-220 | ERECT FABRIC FILTER ID FANS CFB 2 |  |  | 24992 | 0 | 0 | 0 | 24992
[8 empty] | 50951 | 0 | 0 | 0 | 50951 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | STG 1&2 Gen./HP/IP On Fdn Completion | 05 | 05 | 05-68-430-112 | ERECT STG 1 |  |  | 6186 | 0 | 0 | 0 | 6186
m |  | 05 | 05 | 05-68-430-212 | ERECT STG 2 |  |  | 6780 | 0 | 0 | 0 | 6780
[8 empty] | 12966 | 0 | 0 | 0 | 12966 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | STG 1&2 Mechanical Completion | 06 | 06 | 06-13-430-102 | ERECT INTERCONNECTING PIPING STG 1 & 2 |  |  | 16400 | 0 | 0 | 0 | 16400
m |  | 06 | 06 | 06-18-430-102 | ERECT STG 1 & 2 MAIN STRUCTURAL STEEL & STG 1 MISC STRUCTURAL STEEL INCL PAINT TOUCH UP STEEL CFB2 |  |  | 45316 | 0 | 0 | 0 | 45316
m |  | 06 | 06 | 06-68-418-100 | BRIDGE CRANE |  |  | 6736 | 0 | 0 | 0 | 6736
m |  | 06 | 06 | 06-68-430-112 | ERECT STG 1 |  |  | 17153 | 0 | 0 | 0 | 17153
m |  | 06 | 06 | 06-68-430-128 | ERECT FW TANK DEARATOR HEATERS PUMPS FOR STG 1 |  |  | 77597 | 0 | 0 | 0 | 77597
m |  | 06 | 06 | 06-68-430-212 | ERECT STG 2 |  |  | 19846 | 0 | 0 | 0 | 19846
m |  | 06 | 06 | 06-68-430-228 | ERECT FW TANK DEARATOR HEATERS PUMPS FOR STG 2 |  |  | 88325 | 0 | 0 | 0 | 88325
[8 empty] | 271373 | 0 | 0 | 0 | 271373 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | CTG 1&2 Mechanical Completion | 07 | 07 | 07-18-480-002 | ERECT STRUCTURAL STEEL CTG 1 & 2 INCL PAINTING TOUCH UP |  |  | 4163 | 0 | 0 | 0 | 4163
m |  | 07 | 07 | 07-68-480-004 | EQUIPMENT INSTALLATION CTG 1 & 2 |  |  | 56273 | 0 | 4290 | 4290 | 51983 |  |  | 2010-10-30: 715; 2010-11-06: 1210; 2010-11-13: 1260; 2010-11-20: 1105
m |  | 07 | 07 | 07-68-480-008 | EMERGENCY DIESEL GEN SET |  |  | 16224 | 0 | 0 | 0 | 16224
[8 empty] | 76660 | 0 | 4290 | 4290 | 72370 |  |  | 0 | 0 | 0 | 715 | 1210 | 1260 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | BLR 1&2 Piping HT Completion | 08 | 08 | 08-13-420-101 | ERECT BOILER FEED WATER (BFW) PIPING CFB 1 |  |  | 24064 | 0 | 0 | 0 | 24064
m |  | 08 | 08 | 08-13-420-201 | ERECT BOILER FEED WATER (BFW) PIPING CFB 2 |  |  | 24064 | 0 | 0 | 0 | 24064
m |  | 08 | 08 | 08-13-430-101 | NON CRITICAL PIPING UNIT CFB 1 |  |  | 33543 | 0 | 0 | 0 | 33543
m |  | 08 | 08 | 08-13-430-201 | NON CRITICAL PIPING UNIT CFB 2 |  |  | 33545 | 0 | 0 | 0 | 33545
m |  | 08 | 08 | 08-14-411-020 | UNDERGROUND PIPING AND DRAINS (BOILER 1&2)_hydrant |  |  | 540 | 0 | 0 | 0 | 540
[8 empty] | 115756 | 0 | 0 | 0 | 115756 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | STG/CTG 1&2 Piping HT Completion | 09 | 09 | 09-13-420-101 | ERECT BOILER FEED WATER (BFW) PIPING CFB 1 |  |  | 95983 | 0 | 0 | 0 | 95983 |  |  | 2010-10-23: 0
m |  | 09 | 09 | 09-13-420-201 | ERECT BOILER FEED WATER (BFW) PIPING CFB 2 |  |  | 95978 | 0 | 0 | 0 | 95978 |  |  | 2010-10-23: 0
m |  | 09 | 09 | 09-13-430-101 | NON CRITICAL PIPING UNIT CFB 1 |  |  | 58426 | 0 | 0 | 0 | 58426 |  |  | 2010-10-23: 0
m |  | 09 | 09 | 09-13-430-201 | NON CRITICAL PIPING UNIT CFB 2 |  |  | 58426 | 0 | 0 | 0 | 58426 |  |  | 2010-10-23: 0
m |  | 09 | 09 | 09-13-481-101 | PIPING CTG 1 & 2 |  |  | 36156 | 0 | 0 | 0 | 36156 |  |  | 2010-10-23: 0
m |  | 09 | 09 | 09-14-411-020 | UNDERGROUND PIPING AND DRAINS (STG/CTG)_hydrant |  |  | 360 | 0 | 0 | 0 | 360
[8 empty] | 345329 | 0 | 0 | 0 | 345329 |  |  | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m | Mechanical Insulation Completion | 10 | 10 | 10-23-420-127 | BHEL EQUIPMENT & INSULATION CFB 1 |  |  | 75789 | 0 | 0 | 0 | 75789
m |  | 10 | 10 | 10-23-420-277 | BHEL EQUIPMENT & INSULATION CFB 2 |  |  | 75788 | 0 | 0 | 0 | 75788
m |  | 10 | 10 | 10-23-430-027 | INSULATION PIPING & EQUIPMENT STG AND CTG 1 & 2 |  |  | 73600 | 0 | 0 | 0 | 73600
m |  | 10 | 10 | 10-23-480-027 | INSULATION PIPING & EQUIPMENT STG AND CTG 1 & 2 |  |  | 13889 | 0 | 0 | 0 | 13889
[8 empty] | 239066 | 0 | 0 | 0 | 239066 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Civil | 355920 | 66893.2 | 32240 | 99133.2 | 256786.8
c |  | 08 | 08 | 08-14-411-020 | UNDERGROUND PIPING AND DRAINS (BOILER 1&2) |  |  | 32535 | 0 | 0 | 0 | 32535
[8 empty] | 32535 | 0 | 0 | 0 | 32535 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c |  | 09 | 09 | 09-14-411-020 | UNDERGROUND PIPING AND DRAINS (STG/CTG) |  |  | 45725 | 4022 | 5180 | 9202 | 36523 |  |  | 2010-09-18: 1970; 2010-10-16: 2052; 2010-10-23: 855; 2010-10-30: 1020; 2010-11-06: 1055; 2010-11-13: 1080; 2010-11-20: 1170
[8 empty] | 45725 | 4022 | 5180 | 9202 | 36523 |  |  | 1970 | 2052 | 855 | 1020 | 1055 | 1080 | 1170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | STG , STG Bldg. & Dea.1&2 Foundation Completion | 11 | 11 | 11-17-412-110 | TABLE TOP FOUNDATION STG 1 |  |  | 34020 | 19323 | 8840 | 28163 | 5857 |  |  | 2010-09-18: 13737.8; 2010-10-16: 5585.2; 2010-10-23: 1410; 2010-10-30: 2010; 2010-11-06: 1730; 2010-11-13: 1800; 2010-11-20: 1890
c |  | 11 | 11 | 11-17-412-120 | PRECAST FOUNDATIONS STG 1 |  |  | 4022 | 0 | 625 | 625 | 3397 |  |  | 2010-11-06: 170; 2010-11-13: 180; 2010-11-20: 275
c |  | 11 | 11 | 11-17-412-130 | STG 1 FOUNDATION DEAERATOR BAY |  |  | 23123 | 10676 | 1310 | 11986 | 11137 |  |  | 2010-09-18: 6272; 2010-10-16: 4404; 2010-10-23: 990; 2010-10-30: 320
c |  | 11 | 11 | 11-17-412-210 | TABLE TOP FOUNDTIONS STG 2 |  |  | 34023 | 8065 | 7110 | 15175 | 18848 |  |  | 2010-09-18: 6150; 2010-10-16: 1915; 2010-10-23: 660; 2010-10-30: 1290; 2010-11-06: 1840; 2010-11-13: 1800; 2010-11-20: 1520
c |  | 11 | 11 | 11-17-412-220 | STG 2 PRECAST FOUNDATIONS |  |  | 4022 | 0 | 180 | 180 | 3842 |  |  | 2010-10-23: 0; 2010-11-13: 50; 2010-11-20: 130
c |  | 11 | 11 | 11-17-412-230 | STG 2 FOUNDATIONS DEAERATOR BAY |  |  | 8462 | 8013.6 | 1080 | 9093.6 | -631.6 |  |  | 2010-09-18: 2030; 2010-10-16: 5983.6; 2010-10-23: 970; 2010-10-30: 30; 2010-11-06: 80
[8 empty] | 107672 | 46077.6 | 19145 | 65222.6 | 42449.4 |  |  | 28189.8 | 17837.8 | 4030 | 3650 | 3820 | 3830 | 3815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | CTG 1&2 Foundation Work Completion | 12 | 12 | 12-17-480-104 | FOUNDATIONS CTG 1 & 2 |  |  | 18495 | 15674.2 | 175 | 15849.2 | 2645.8 |  |  | 2010-09-18: 15339.6; 2010-10-16: 334.6; 2010-11-06: 135; 2010-11-13: 40
[8 empty] | 18495 | 15674.2 | 175 | 15849.2 | 2645.8 |  |  | 15339.6 | 334.6 | 0 | 0 | 135 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c | Other Foundation Work Completion | 13 | 13 | 13-14-411-020 | UNDERGROUND PIPING AND DRAINS |  |  | 17939 | 0 | 360 | 360 | 17579 |  |  | 2010-11-06: 135; 2010-11-13: 170; 2010-11-20: 55
c |  | 13 | 13 | 13-17-403-111 | FOUNDATION BOP IN BOILER AREA: CFB1 |  |  | 65523 | 0 | 0 | 0 | 65523
c |  | 13 | 13 | 13-17-412-120 | PRECAST FOUNDATIONS STG 1 |  |  | 854 | 0 | 0 | 0 | 854
c |  | 13 | 13 | 13-17-412-130 | STG 1 FOUNDATION DEAERATOR BAY |  |  | 6691 | 0 | 1500 | 1500 | 5191 |  |  | 2010-10-30: 320; 2010-11-06: 570; 2010-11-13: 430; 2010-11-20: 180
c |  | 13 | 13 | 13-17-412-220 | STG 2 PRECAST FOUNDATIONS |  |  | 854 | 0 | 0 | 0 | 854
c |  | 13 | 13 | 13-17-412-230 | STG 2 FOUNDATIONS DEAERATOR BAY |  |  | 6691 | 0 | 740 | 740 | 5951 |  |  | 2010-10-30: 740
c |  | 13 | 13 | 13-17-413-211 | FOUNDATION BOP IN BOILER AREA: CFB2 |  |  | 52941 | 1119.4 | 5140 | 6259.4 | 46681.6 |  |  | 2010-10-16: 1119.4; 2010-10-23: 790; 2010-10-30: 720; 2010-11-06: 1030; 2010-11-13: 1490; 2010-11-20: 1110
[8 empty] | 151493 | 1119.4 | 7740 | 8859.4 | 142633.6 |  |  | 0 | 1119.4 | 790 | 1780 | 1735 | 2090 | 1345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | E&I | 411045 | 1879.2 | 340 | 2219.2 | 408825.8
E | Electrical Work Completion | 14 | 14 | 14-16-400-001 | POWER STATION AREA 400 BURIED GROUNDING |  |  | 2808 | 1879.2 | 315 | 2194.2 | 613.8 |  |  | 2010-09-18: 1088; 2010-10-16: 791.2; 2010-10-23: 245; 2010-11-06: 30; 2010-11-20: 40
E |  | 14 | 14 | 14-16-420-103 | ELECTRICAL CFB1 (INCL AUXILLARIES AND LIGHTNING PROTECTION) |  |  | 40615 | 0 | 25 | 25 | 40590 |  |  | 2010-10-23: 25
E |  | 14 | 14 | 14-16-420-203 | ELECTRICAL CFB2 (INCL AUXILLARIES AND LIGHTNING PROTECTION) |  |  | 40583 | 0 | 0 | 0 | 40583
E |  | 14 | 14 | 14-16-430-103 | ELECTRICAL STG1 (INCL AUXILLARIES AND LIGHTNING PROTECTION) |  |  | 29065 | 0 | 0 | 0 | 29065
E |  | 14 | 14 | 14-16-430-203 | ELECTRICAL STG2 (INCL AUXILLARIES AND LIGHTNING PROTECTION) |  |  | 25193 | 0 | 0 | 0 | 25193
E |  | 14 | 14 | 14-16-480-003 | ELECTRICAL CTG 1 & 2 (INCL AUXILLARIES AND LIGHTNING PROTECTION) |  |  | 12577 | 0 | 0 | 0 | 12577
[8 empty] | 150841 | 1879.2 | 340 | 2219.2 | 148621.8 |  |  | 1088 | 791.2 | 270 | 0 | 30 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | Instrumentation Work Completion | 15 | 15 | 15-15-420-110 | INSTRUMENT AND CONTROLS CFB 1 |  |  | 60397 | 0 | 0 | 0 | 60397
E |  | 15 | 15 | 15-15-420-210 | INSTRUMENT AND CONTROLS CFB 2 |  |  | 59392 | 0 | 0 | 0 | 59392
E |  | 15 | 15 | 15-15-430-110 | INSTRUMENT AND CONTROLS STG 1 |  |  | 52117 | 0 | 0 | 0 | 52117
E |  | 15 | 15 | 15-15-430-210 | INSTRUMENT AND CONTROLS STG 2 |  |  | 52092 | 0 | 0 | 0 | 52092
E |  | 15 | 15 | 15-15-480-120 | INSTRUMENT AND CONTROLS CTG 1 & 2 |  |  | 36206 | 0 | 0 | 0 | 36206
[8 empty] | 260204 | 0 | 0 | 0 | 260204 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total CWP | [5 empty] | 3077899 | 126281.8 | 77865 | 204146.8 | 2873752.2 |  |  | 76236.8 | 48025 | 11030 | 13540 | 15410 | 15885 | 16820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Description | [5 empty] | Total Dmhr | Up to Last Month | Man Hours |  |  | Remark |  | 2010-10-23: 16540; 2010-10-30: 18640; 2010-11-06: 19570; 2010-11-13: 20125; 2010-11-20: 21180
[10 empty] | Actual | To Date | To Go
|  | Civil | [5 empty] | 355920 | 66893.2 | 32240 | 99133.2 | 256786.8
|  | Mechanical | [5 empty] | 2310934 | 57509.4 | 45285 | 102794.4 | 2208139.6
|  | Electrical | [5 empty] | 411045 | 1879.2 | 340 | 2219.2 | 408825.8
|  | Total | [5 empty] | 3077899 | 126281.8 | 77865 | 204146.8 | 2873752.2
Note on T2: Put in the cutoff date Number of weeks in this month

## variation (Monthly)
Cut Off | 2010-11-26 | 2010-10-22
Weeks | 5
Extra Work DMHR Status - Month of Nov
Koniambo Power Station (C004) - Doosan |  |  |  |  | 2010-11-26
Discipline | Code | Description | Up to Last Month | Man Hours |  | This Month | Remark | Total | 2010 | [32 empty] | 2011 | [52 empty] | 2012
|  |  |  | This Month | to Date |  |  |  | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
 | time axis 2010-05-15 to 2012-07-28
Civil | VPR 007 | STG 1 Table top lean concrete | 284 | 0 | 284 | 0 |  | 284 | 2010-07-03: 284
| VPR 007 | STG 2 Table top lean concrete | 458 | 0 | 458 | 0 |  | 458 | 2010-07-10: 258; 2010-07-17: 200
| VNR 020 | EDG 1&2 lean concrete | 458 | 0 | 458 | 0 |  | 458 | 2010-07-31: 458
| VNR 020 | STG 1&2 Deaerator bay lean concrete | 1735 | 0 | 1735 | 0 |  | 1735 | 2010-08-28: 530; 2010-09-04: 845; 2010-09-25: 220; 2010-10-02: 140
| VNR 020 | Lean Concrete for Precast Foundations STG 1 & 2 | 0 | 450 | 450 |  |  | 450 | 2010-11-13: 230; 2010-11-20: 220
| VNR 020 | Lean Concrete for Cast-in-situ Foundation STG 1 & 2 | [6 empty] | 2010-11-20: 50
| VNR 045 | Completion of STG 1 & 2 De-bay Micropile | [6 empty] | 2010-11-20: 140
| VNR 020 | CFB #2 ID Fan & Stack duct support FDN Lean | 727 | 0 | 727 | 0 |  | 727 | 2010-10-02: 260; 2010-10-16: 467
| VNR 016 | Lay down area OIL storage FDN | 55 | 60 | 115 | 60 |  | 115 | 2010-09-04: 55; 2010-10-23: 60
| VNR 018 | Boiler 1&2 FBHE Support FDN | 1430 | 0 | 1430 | 0 |  | 1430 | 2010-09-25: 810; 2010-10-02: 620
| VNR 021 | CFB #2 Onsite office FDN | 0 | 260 | 260 | 260 |  | 260 | 2010-10-23: 60; 2010-10-30: 200
Sub total |  |  | 5147 | 770 | 5917 | 320 |  | 5917 | 2010-05-15: 0; 2010-05-22: 0; 2010-05-29: 0; 2010-06-05: 0; 2010-06-12: 0; 2010-06-19: 0; 2010-06-26: 0; 2010-07-03: 284; 2010-07-10: 258; 2010-07-17: 200; 2010-07-24: 0; 2010-07-31: 458; 2010-08-07: 0; 2010-08-14: 0; 2010-08-21: 0; 2010-08-28: 530; 2010-09-04: 900; 2010-09-11: 0; 2010-09-18: 0; 2010-09-25: 1030; 2010-10-02: 1020; 2010-10-09: 0; 2010-10-16: 467; 2010-10-23: 120; 2010-10-30: 200; 2010-11-06: 0; 2010-11-13: 230; 2010-11-20: 410
Mech. | VNR 023 | Unpacking Boxes | 3244 | 960 | 4204 | 960 |  | 4204 | 2010-08-28: 400; 2010-09-04: 300; 2010-09-11: 300; 2010-09-18: 250; 2010-09-25: 390; 2010-10-02: 540; 2010-10-09: 660; 2010-10-16: 404; 2010-10-23: 480; 2010-10-30: 480
| VNR 023 | EK Laydown Warehouse (Site Area) man-supply | 0 | 710 | 710 | 710 |  | 710 | 2010-11-06: 240; 2010-11-13: 230; 2010-11-20: 240
| VNR 023 | EK Laydown manpower assist for dismantle of temp. stiffener | 0 | 720 | 720 | 720 |  | 720 | 2010-11-06: 240; 2010-11-13: 240; 2010-11-20: 240
| VNR 037 | Supply of 5scaffolders | 0 | 2590 | 2590 | 2590 |  | 2590 | 2010-10-23: 370; 2010-10-30: 600; 2010-11-06: 540; 2010-11-13: 540; 2010-11-20: 540
| RFI 100004 | Misslignment of bolt holes on girder | 0 | 1800 | 1800 | 1800 |  | 1800 | 2010-10-23: 360; 2010-10-30: 360; 2010-11-06: 360; 2010-11-13: 360; 2010-11-20: 360
| RFI 100007 | 2 creat angles for girders is longer than column width | 0 | 1800 | 1800 | 1800 |  | 1800 | 2010-10-23: 360; 2010-10-30: 360; 2010-11-06: 360; 2010-11-13: 360; 2010-11-20: 360
| RFI 100008 | Top Paint is coated on surface bolt connection | 0 | 1800 | 1800 | 1800 |  | 1800 | 2010-10-23: 360; 2010-10-30: 360; 2010-11-06: 360; 2010-11-13: 360; 2010-11-20: 360
| RFI 100009 | Top Paint is coated on surface for field welding | 0 | 1800 | 1800 | 1800 |  | 1800 | 2010-10-23: 360; 2010-10-30: 360; 2010-11-06: 360; 2010-11-13: 360; 2010-11-20: 360
| RFI 100013 | Irregularity of column base for coal bunker | 0 | 100 | 100 | 100 |  | 100 | 2010-10-23: 100
Sub total |  |  | 3244 | 12280 | 15524 | 12280 |  | 15524 | 2010-05-15: 0; 2010-05-22: 0; 2010-05-29: 0; 2010-06-05: 0; 2010-06-12: 0; 2010-06-19: 0; 2010-06-26: 0; 2010-07-03: 0; 2010-07-10: 0; 2010-07-17: 0; 2010-07-24: 0; 2010-07-31: 0; 2010-08-07: 0; 2010-08-14: 0; 2010-08-21: 0; 2010-08-28: 400; 2010-09-04: 300; 2010-09-11: 300; 2010-09-18: 250; 2010-09-25: 390; 2010-10-02: 540; 2010-10-09: 660; 2010-10-16: 404; 2010-10-23: 2390; 2010-10-30: 2520; 2010-11-06: 2460; 2010-11-13: 2450; 2010-11-20: 2460
Elec.
Sub total | [8 empty] | 2010-11-13: 0
TOTAL EXTRA HOURS |  |  | 8391 | 13050 | 21441 | 12600 |  | 21441 | 2010-05-15: 0; 2010-05-22: 0; 2010-05-29: 0; 2010-06-05: 0; 2010-06-12: 0; 2010-06-19: 0; 2010-06-26: 0; 2010-07-03: 284; 2010-07-10: 258; 2010-07-17: 200; 2010-07-24: 0; 2010-07-31: 458; 2010-08-07: 0; 2010-08-14: 0; 2010-08-21: 0; 2010-08-28: 930; 2010-09-04: 1200; 2010-09-11: 300; 2010-09-18: 250; 2010-09-25: 1420; 2010-10-02: 1560; 2010-10-09: 660; 2010-10-16: 871; 2010-10-23: 2510; 2010-10-30: 2720; 2010-11-06: 2460; 2010-11-13: 2680; 2010-11-20: 2870
TOTAL HOURS INDIRECT
|  | TOTAL HOURS DIRECT +INDIRECT | [6 empty] | 2010-05-15: 0; 2010-08-28: 930; 2010-09-04: 1200; 2010-09-11: 300; 2010-09-18: 250; 2010-09-25: 1420; 2010-10-02: 1560; 2010-10-09: 660; 2010-10-16: 871; 2010-10-23: 2510; 2010-10-30: 2720; 2010-11-06: 2460
Signature of Contractor
Note on C2: Put in the cutoff date Number of weeks in this month

## Infrastructural (Monthly)
Cut Off | 2010-11-26 | 2010-10-22
Weeks | 5
Infrastructural Work Man Hours Status
Koniambo Power Station (C004) - Doosan |  |  |  |  | 2010-11-26
Discipline | Code | Description | Up to Last Month | Man Hours |  | This Month | Remark | Total | 2010 | [32 empty] | 2011 | [52 empty] | 2012
|  |  |  | This Month | to Date |  |  |  | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30
 | time axis 2010-05-15 to 2012-07-28
Civil |  | Laydown area gas storage FDN | 1032.6 | 1820 | 2852.6 | 1820 |  | 2852.6 | 2010-08-14: 110; 2010-09-04: 110; 2010-10-09: 320; 2010-10-16: 492.6; 2010-10-23: 990; 2010-10-30: 650; 2010-11-06: 180
|  |  | 0 | 0 | 0 | 0 |  | 0
|  |  | 0 | 0 | 0 | 0 |  | 0
Sub total |  |  | 1032.6 | 1820 | 2852.6 | 1820 |  | 2852.6 | 2010-05-15: 0; 2010-05-22: 0; 2010-05-29: 0; 2010-06-05: 0; 2010-06-12: 0; 2010-06-19: 0; 2010-06-26: 0; 2010-07-03: 0; 2010-07-10: 0; 2010-07-17: 0; 2010-07-24: 0; 2010-07-31: 0; 2010-08-07: 0; 2010-08-14: 110; 2010-08-21: 0; 2010-08-28: 0; 2010-09-04: 110; 2010-09-11: 0; 2010-09-18: 0; 2010-09-25: 0; 2010-10-02: 0; 2010-10-09: 320; 2010-10-16: 492.6; 2010-10-23: 990; 2010-10-30: 650; 2010-11-06: 180
Mech. |  | Laydown gas storage for common use | 4677.8 | 0 | 4677.8 | 0 |  | 4677.8 | 2010-08-28: 90; 2010-09-04: 417.8; 2010-09-11: 420; 2010-09-18: 750; 2010-09-25: 900; 2010-10-02: 900; 2010-10-09: 900; 2010-10-16: 300
|  | Tool Box (Archive) & Welding Production | 0 | 1920 | 1920 | 1920 |  | 1920 | 2010-10-30: 1020; 2010-11-06: 300; 2010-11-13: 300; 2010-11-20: 300
|  | Container Box Relocation Preparation & Generator Pedestal Production | 321 | 1800 | 2121 | 1800 |  | 2121 | 2010-10-16: 321; 2010-10-23: 540; 2010-11-06: 420; 2010-11-13: 420; 2010-11-20: 420
|  | Man assist for crane company | 2730 | 600 | 3330 | 600 |  | 3330 | 2010-09-04: 360; 2010-09-11: 360; 2010-09-18: 360; 2010-09-25: 240; 2010-10-02: 360; 2010-10-09: 520; 2010-10-16: 530; 2010-10-23: 600
|  | Water Fountain (Water Bucket) Production | 99 | 30 | 129 | 30 |  | 129 | 2010-10-16: 99; 2010-10-23: 30
|  | Fire Extinguisher Pedestal Production | 0 | 150 | 150 | 150 |  | 150 | 2010-10-23: 150
|  | Man assist for scaffolding | 125 | 0 | 125 | 0 |  | 125 | 2010-10-16: 125
|  | Laydown Fence installation work | 370 | 0 | 370 | 0 |  | 370 | 2010-09-25: 180; 2010-10-02: 160; 2010-10-09: 30
|  |  | 0 | 0 | 0 | 0 |  | 0
Sub total |  |  | 8322.8 | 4500 | 12822.8 | 4500 |  | 12822.8 | 2010-05-15: 0; 2010-05-22: 0; 2010-05-29: 0; 2010-06-05: 0; 2010-06-12: 0; 2010-06-19: 0; 2010-06-26: 0; 2010-07-03: 0; 2010-07-10: 0; 2010-07-17: 0; 2010-07-24: 0; 2010-07-31: 0; 2010-08-07: 0; 2010-08-14: 0; 2010-08-21: 0; 2010-08-28: 90; 2010-09-04: 777.8; 2010-09-11: 780; 2010-09-18: 1110; 2010-09-25: 1320; 2010-10-02: 1420; 2010-10-09: 1450; 2010-10-16: 1375; 2010-10-23: 1320; 2010-10-30: 1020; 2010-11-06: 720; 2010-11-13: 720; 2010-11-20: 720
Elec. |  | Temporary Power Supply | 7959 | 3810 | 11769 | 3810 |  | 11769 | 2010-07-31: 780; 2010-08-07: 550; 2010-08-14: 420; 2010-08-21: 720; 2010-08-28: 760; 2010-09-04: 690; 2010-09-11: 710; 2010-09-18: 540; 2010-09-25: 765; 2010-10-02: 750; 2010-10-09: 625; 2010-10-16: 649; 2010-10-23: 690; 2010-10-30: 710; 2010-11-06: 800; 2010-11-13: 840; 2010-11-20: 770
|  |  | 0 | 0 | 0 | 0 |  | 0
Sub total |  |  | 7959 | 3810 | 11769 | 3810 |  | 11769 | 2010-05-15: 0; 2010-05-22: 0; 2010-05-29: 0; 2010-06-05: 0; 2010-06-12: 0; 2010-06-19: 0; 2010-06-26: 0; 2010-07-03: 0; 2010-07-10: 0; 2010-07-17: 0; 2010-07-24: 0; 2010-07-31: 780; 2010-08-07: 550; 2010-08-14: 420; 2010-08-21: 720; 2010-08-28: 760; 2010-09-04: 690; 2010-09-11: 710; 2010-09-18: 540; 2010-09-25: 765; 2010-10-02: 750; 2010-10-09: 625; 2010-10-16: 649; 2010-10-23: 690; 2010-10-30: 710; 2010-11-06: 800; 2010-11-13: 840; 2010-11-20: 770; 2010-11-27: 0; 2010-12-04: 0; 2010-12-11: 0; 2010-12-18: 0; 2010-12-25: 0; 2011-01-01: 0; 2011-01-08: 0; 2011-01-15: 0; 2011-01-22: 0; 2011-01-29: 0; 2011-02-05: 0
TOTAL INFRASTRUCTURAL HOURS |  |  | 17314.4 | 10130 | 27444.4 | 10130 |  | 27444.4 | 2010-05-15: 0; 2010-05-22: 0; 2010-05-29: 0; 2010-06-05: 0; 2010-06-12: 0; 2010-06-19: 0; 2010-06-26: 0; 2010-07-03: 0; 2010-07-10: 0; 2010-07-17: 0; 2010-07-24: 0; 2010-07-31: 780; 2010-08-07: 550; 2010-08-14: 530; 2010-08-21: 720; 2010-08-28: 850; 2010-09-04: 1577.8; 2010-09-11: 1490; 2010-09-18: 1650; 2010-09-25: 2085; 2010-10-02: 2170; 2010-10-09: 2395; 2010-10-16: 2516.6; 2010-10-23: 3000; 2010-10-30: 2380; 2010-11-06: 1700; 2010-11-13: 1560; 2010-11-20: 1490; 2010-11-27: 0; 2010-12-04: 0; 2010-12-11: 0; 2010-12-18: 0; 2010-12-25: 0; 2011-01-01: 0; 2011-01-08: 0; 2011-01-15: 0
TOTAL HOURS INDIRECT
|  | TOTAL HOURS DIRECT +INDIRECT | [6 empty] | 2010-05-15: 0; 2010-08-28: 850; 2010-09-04: 1577.8; 2010-09-11: 1490; 2010-09-18: 1650; 2010-09-25: 2085; 2010-10-02: 2170; 2010-10-09: 2395; 2010-10-16: 2516.6; 2010-10-23: 3000; 2010-10-30: 2380; 2010-11-06: 1700
Signature of Contractor
Note on C2: Put in the cutoff date Number of weeks in this month